## Open
Bugs in maucisynth
Next ID	9

ID	Description	Priority	Found	Fixed	Comment
6	Sawtooth and pulse waves sound louder than other waveforms. Find optimal amplitude by Fourier analysis.	0	01.04.12		Lowpass filter can soften this aesthetic problem.

3	Suddenly worsening cracking with multiple notes playing, finally JACK xrun	0	01.04.12		This also happens with other JACK software synths like Bristol. Linux kernel with realtime patches, like in Ubuntu Studio, is probably required.

## Fixed
Fixed bugs

ID	Description	Priority	Found	Fixed
1	Envelope: note keeps playing when A=100, R=5, bufferLength=128, fast note on-off	5	01.04.12	01.04.12
4	note retriggering to work properly	5	01.04.12	01.04.12
7	Already ended notes were retriggered to RELEASE phase at note off	4	04.04.12	04.04.12
8	LFO initial value was out of range	5	06.04.12	06.04.12
9	Wrong initial frequency on lowpass filter	5	06.05.12	06.05.12

## Unknown
Bugs that don't seem appear any more
ID	Description	Priority	Found	Fixed	Comment
2	MainOscillator: !(-1 <= angle <= 1) after synthesizeFromWavetable	5	01.04.12
5	Crash on startup, but only sometimes	5	01.04.12